INTERPRETING THE RULES OF STANDARD METHOD OF RESOURCE SCHEDULING 1  (SMRS 1)

BEING A PAPPER PRESENTED

AT THE NIGERIAN INSTITUTE OF QUANTITY SURVEYORS (NIQS) ORGANIZED WORKSHOP TITLED : IMPORTANCE OF RESOURCE SCHEDULE FOR EXCLUSIVE DEVELOPMENT OF THE CONSTRUCTION INDUSTRY

FOR “ TRAIN THE TRAINERS”

DATE :	 MONDAY 29TH  -  TUESDAY 30TH MARCH, 2021

VENUE : 	VISUAL

TIME :    	9:00AM – 5:00PM

BY

PROF. S. I.J ONWUSONYE. FNIQS. CCArb

DEPARTMENT OF QUANTITY SURVEYING

IMO STATE UNIVERSITY, OWERRI

08033616695

MARCH, 2021

INTERPRETING THE RULES OF STANDARD METHOD OF RESOURCE SCHEDULING 1 (SMRS 1)

1.0	The Standard Method of Resource Scheduling I (SMRSI)

1.1	Introduction

The Standard Method of Resource Scheduling I (SMRSI) is a reference text, designed to guide key players in the construction industry especially the Quantity Surveyors to produce Construction Resource and Economy Schedule (CORES) (Onwusonye, 2018).

Construction project relies on method statement for effective and efficient delivery.

Method Statement, CEM (2019), is a document which indicates the main items of work to be performed, together with the main item of plant and labour required.  It does indicate the order in which it is necessary to carry out certain key items of work and the expected time for each activity if the resources suggested are used.

Resource scheduling in the construction industry seeks to showcase in details, the ingredients of materials, labour, and plant underpinned by time dimensions.

However, construction project possesses series of activities which among others consume time individually.  The time needed to realize a given activity varies and depends on the complexity, technology, location and uninterrupted flow of funds to the activity(s), among others.

Furthermore, while some activities follow one another in constructive order, others are simply independent and can be carried out simultaneously.  Each of these cases has its own time requirements and associated resource implications.

The calculations and presentation of Construction Resource Scheduling are highly technical, and require expertise, experience, consultations and even references.

In Nigeria there has not been any text for standardized presentation and/or format of Resource Scheduling until August, 2006 when the Nigerian Institute of Quantity Surveyors published the Standard Method of Resource Scheduling I (SMRSI) which provided  guide for  relevant professionals to produce the Construction Resource And Economy Schedule (CORES)

1.2	The NEED

The formal sector favours the use of Bills of Quantities, a complex and professionally designed document showcasing synthesis of all materials, plant and labour contents of the construction processes as elements with cost implications expressed in rates.

Most clients especially of  the secondary categories are not at home with the compound nature of rates and in line with the contractual requirements of the formal sector project procurement, consultants effect rates as tools for planning and controlling of materials, plant and labour with little or no reference to the clients inputs.

This attitude is tolerated in the formal sector perhaps, as most clients serve as employers and are compelled by the nature of project finance such as public funds and/or other sources of external project funding, to honour and settle valuation(s)/certificates and hence apparently gloss over their natural desire of dictating the tune especially in the purchase of materials, and control of plants and labour contents.

Interestingly, this factor seems to explain why some projects procured in this sector often suffer interrupted flow of funds leading to abandonment, litigation, cost and time overruns.

The informal sector refers to activities effected not in conformity with the usual or prescribed form and are unofficial.

It follows that the informal sector is deficient in the compliance of laid down rules, government policies, actions and guidelines associated with project procurement processes in the formal sector.

The informal sector operations, no doubt, have continuously created enormous strains and leakages on the construction processes while the bills of quantities of the formal sector is traditionally bureaucratic with overwhelming restraining forces.

Hence, the need for a highly organic document, capable of responding very rapidly to the demands of the informal sector and whose attributes are poised to overtake the identified restraining forces of the formal sector towards macro efficiency of the construction industry. The Standard Method of Resource Scheduling I is the document.

1.3	The Construction Resource and Economy Schedule (CORES)

The Construction Resource and Economy Schedule (CORES) Onwusonye (2018), is a professionally prepared document which seeks to technically exhibit easily interpretable data relating to the schedule for timely and economic order quantity of materials, plant and labour essentially needed in any construction activities and whose cost implications are expressed in prices.

1.3.1	Primary Data

Primarily, the Bills of Quantities is needed towards obtaining information on the quantum of work (major elements) considered relevant in the calculation of labour, materials and plant schedules while the Bar Chart and Network Diagrams techniques shall be required for the integration of time needed by each item of work, and by extension, the entire project including the effect(s) of associated delays on each activity and/or critical activities.

1.3.2	Rules with Illustration

Illustrations

This paper shall dwell on the production of CORES for labour scheduling of a typical project, using SMRS 1 as a guide.

Data

Data generated seek to showcase the amount of work ( quantity) to be done, nature of work ( quality) to be done and the duration for each of the activities (Time) to do it and by implication, the time to actualize the entire project.

The data for quantity is obtainable from the Bills of Quantities (BOQ), quality is obtained from specifications while the time duration is obtained from cost analyses and / or as adjusted.

Furthermore, this work shall base its calculation(s) on  five(5) day working week and eight(8) hour working day. In addition, a 40:60 skilled and unskilled labour input ratio has been effected including some other varying (relative) man-hour or gang day labour output.

(i)	Clear Site: January.  (1520m2) 4 weeks.

If output per unskilled labour day 	=	12.96m2 (constant)

1520m2 will take 117.28 days ie (1520/12.96)

Time period allowed	=	4 x 5 	=	20 days

Hence, total: 117.28/20	=	5.86

Thus, 6 unskilled labour.

(ii)	Accommodation (Temporary)  February (120m2) 4 weeks

If output per gang day	=	4m2 (Constant)

120m2 will take: 30 gang days (120/4)

Time period allowed 	=   	4 x 5	=	20 days

Hence: 30/20		=	1.5

Thus:  skilled		=	2

Unskilled		=	3

(iii)	Excavation:  February (240m3) 4 weeks

If output 	=	2 unskilled hour per m3 (Constant)

1 unskilled hour per 0.5m3

Hence, 4m3 for 8 unskilled hours or 1 day

Time allowed 	= 4 x 5 x 8	=  160 hours or	20 days

240m3	= 240/80	=	3 ie 160/0.5m3 per unskilled  = 80

Hence,  3  unskilled men

(iv)	Infrastructure:  March  4 weeks

If output  =  1 Nr per week/gangs =  2 unskilled/week and

1 skilled/week

Hence: 4 gang weeks

skilled		=	4

Unskilled		=	8

(v)	Blockwork:  March (2500m2) 3 weeks

If output = 140 blocks per gang day (Constant)

But 2500m2 contains 2500 x 9	=     22500 blocks  ie 9blocks/m2 wall

Thus, 2500m2	=    161 gang days

Time allowed 	=     3 x 5	=	15 days

Hence:  161/15	=    10.7	=	11 gangs

Thus, 11  skilled, 17 unskilled.

(vi)	Formwork:  April (400m2)  4 weeks

If output is 4m2 per gang day

Then, 400m2 will take: 100 gang days

Time allowed 		=   	4 x 5	=	20 days

=> 100/20		=    5  gangs

Hence:   5   skilled

8   Unskilled

(vii)	Reinforcement:  March  (9 tons) 4 weeks

If output  =   192kg per gang day

=> 9 tons = 9 x 1000/192   =  46.88 gang days

Time allowed 		=   	5 x 4	=	20 days

Hence: 4.688/20	=	2.34 gangs

Thus:  skilled		=	3

Unskilled		=	5

(vii)	Backfill: March – April  (650m2) 2 weeks

If output   =   1.25m for 1 unskilled hour

For 650m3   =  520 unskilled man hour

Time allowed 		=   2 x 5 x 8	=	80 hours

Hence: 520/80		=	7 unskilled men

(ix)	Concrete (substructure)  May 250m3  2 weeks

If output   =  1.25m3 gang hours

For 250m3		=	200 gang hours

Time allowed 		=   	80 hours

Hence: 200/80		=	3 gangs

Thus:  3 skilled,  5 unskilled

(x)   	Frame  May – June  700m3	5 weeks

If  1 gang hour output	=	0.97m3

=> 700m2	=	722  gang hours

But  5 weeks	=	200 gang hours

Hence,  722	=	4 gangs

Thus:   4  skilled and   6  unskilled.

(xi)	Finishings:  June – July  3000m2   4 weeks

If gang day output 1 	=	20m2

Then, 3000m2		=	150 gang days

Time allowed 		=   	20 days

Hence,   8 gangs

Hence: 30/20		=	1.5

Thus:    8  skilled and   12  unskilled

(xii)	Roof:  June – July  (1650m2)  4 weeks

If output 	=	25m2  gang day

=> 1650m2	=	66 gang days

Allowed time	=   	20 days

Hence:  4  gangs

Thus:   4  skilled and  6  Unskilled

(xiii)	External Works:   April  (950m2)  2  weeks

If output gang day	=	20m2

=> 950m2	=	48 gang days

Allowed time	=   	10 days

Hence:  5  gangs

Thus:   5  skilled and  8  Unskilled

(xiv)	Tarmac:   July – August   (170m2)  4 weeks

If output 	=	6m2  gang day

=> 170m2	=	29 gang days

Time Allowed	=   	20 days

Hence:  2  gangs

Thus:   2  skilled  and  3  Unskilled

(xv)	Cleaning:    July  (35m2)  1 week

1	unskilled man output	=	7m3  daily

Hence:  1 Unskilled for 5 days

The above calculations are hereby expressed in a table as shown below

| Activity | # Description | Time period | Skilled | Unskilled |
| --- | --- | --- | --- | --- |
| 1-2 | Clear Site | Jan. (4 weeks) | - | 6 |
| 2-3 | # Temporary Accommodation | February 4 weeks | 2 | 3 |
| 2-3 | # Excavation | February 4 weeks | - | 3 |
| 3-5 | Infrastructure | March 4 weeks | 1 | 3 |
| 4-6 | Block work | March 3 weeks | 11 | 17 |
| 4-7 | Reinforcement k | March 4 weeks | 3 | 5 |
| 6-8 | Backfill | March – April 2 weeks | - | 7 |
| 7-8 | Formwork | April 4 weeks | 5 | 8 |
| 8-9 | Concrete work (Substructure) | May 2 weeks | 3 | 5 |
| 9-10 | Frame | May – June 5 weeks | 4 | 6 |
| 10-11 | Finishings | June – July 4 weeks | 8 | 12 |
| 10-12 | Roof | June – July 4 weeks | 4 | 6 |
| 5-13 | External works | April 2 weeks | 5 | 8 |
| 11-13 | Tarmac | July – August 4 weeks | 2 | 3 |
| 12-13 | Clearing | July 1 week | - | 1 |
| 13-14 | Testing | August 1 week | 1 | 1 |
| 14-15 | Handover | September 1 week | 1 | 1 |
| TOTAL LABOUR REQUIREMENTS |  |  | 50 | 94 |

Rules

Interpreting the rules for the applications of Standard Method Of Resource Scheduling 1 (SMRS) to produce the Construction Resource And Economy Schedule (CORES) of labour are as graphically presented and explained

CONSTRUCTION RESOURCE AND ECONOMY SCHEDULE

(CORES) FOR KNOWLEDGE ABODE, OWERRI

PRELIMINARIES AND GENERAL ITEMS

| WORK DESCRIPTION |  | EMPLOYER’S RESPONSIBILITY | CONTRACTOR’S RESPONSIBILITY |  |
| --- | --- | --- | --- | --- |
|  |  |  | Method Statement and Charge |  |
| 1. Project Particulars | 1. Name of project and Location 2. Names and addresses of Employers and consultants | New Haven Lodge New Owerri JISED LTD. and Network Projects Nigeria |  |  |
| 2. Tender & Contract documents | 1. List of drawings used for preparing the Schedule 2. List of drawings to be used for the contract 3. Form of Contract used | AD1 – 6 Same above Labour only |  |  |
| 3. Insurance | 1. Insurance of the works 2. Third party | Employer’s responsibility |  |  |
| 4. Temporary Accommodation | 120m2 Gross Floor Area (GFA) |  | 20 gang days 2 capenters @ N1784 3 Labourers @ N1440 | N71360.00 N86400.00 |
| Preliminaries And General Items carried to Summary |  |  |  | N15776.00 |

CONSTRUCTION RESOURCE AND ECONOMY SCHEDULE  (CORES)

| ITEM REF: NO | WORK SECTION/ ELEMENT DESCRIPTION | EMPLOYER’S RESPONSIBILITY |  |  |  |  | CONTRACTOR’S RESPONSIBILITY |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Materials | Qty | Unit | Price | Amount N K |  |
| 1. | Site Preparation/Earthwork Clear site |  | 1520 | M2 |  |  | 20 days 1.1 Labourers @ N1440.00 = 172800.00 |
| 2. | Excavation foundation trenches and column bases |  | 240 | M3 |  |  | N172800.00 |
|  |  |  |  |  |  |  | 20 days 3 labourer @ N1440.00 = N86400 |
|  |  |  |  |  |  |  | N86400.00 |
| 5 | Backfilling Excavations | Laterite | 650 | M3 |  |  | 10 days 1.1 7 labourers @ N1440.00 = N100800 |
|  |  |  |  |  |  |  | N100800 |
|  | Page Total | Topsoil Excavation Backfilling To Summary |  |  |  |  | N172800 N86400 N100800 |
|  |  |  |  |  |  |  | N360,000.00 |

CONSTRUCTION RESOURCE AND ECONOMY SCHEDULE  (CORES)CONTD.

| ITEM REF: NO | WORK SECTION/ ELEMENT DESCRIPTION | EMPLOYER’S RESPONSIBILITY |  |  |  |  | CONTRACTOR’S RESPONSIBILITY |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Materials | Qty | Unit | Price | Amount N K |  |
| 2 | In-situ Concrete And Precast Concrete Foundation (1:2:4) (250m3) |  | 1543 29 22 | Bags trips trips |  |  | 10 gang days 1.1 3 Masons @ N 1784 = N53520 1.2 5 labourers @ N1440 = N72,000.00 2.1 2Nr Mixer @ N7000 = N140,000.00 2.2 2Nr vibrator @ N300.00 = N60,000 |
|  |  |  |  |  |  |  | N277352.00 |
| 7 | Frame (1:2:4) (700m3) |  | 4320 79 60 | Bags trips trips |  |  | 25 gang days 1.1 4 Masons @ N 1784 = N178400 1.2 6 labourers @ N1440 = N21600 2.1 2Nr Mixer @ N7000 =N360,000.00 2.2 2Nr vibrator @ N3000 = N150,000 |
|  |  |  |  |  |  |  | N904,400 |
| 11 11.1 | Transport Handling Charges |  | 5863 “ | Bags “ |  |  |  |
|  | Page Total |  | 5863 108 82 - - | bags trips trips - - |  |  |  |
| Concrete Carried To Summary |  |  |  |  |  |  | N1181752.00 |

CONSTRUCTION RESOURCE AND ECONOMY SCHEDULE  (CORES)CONTD.

| ITEM REF: NO | WORK SECTION/ ELEMENT DESCRIPTION | EMPLOYER’S RESPONSIBILITY |  |  |  |  | CONTRACTOR’S RESPONSIBILITY |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Materials | Qty | Unit | Price | Amount N K |  |
|  | Formwork Sides and soffits of sills, lintel Sides of columns Miscellaneous Transport Handling Charges Abils | Wood Nails Wood Wood Nail | 370 20 370 370 20 | lengths bags lengths lengths bags |  |  | 20 gang days 1.1 5 carpenters @ N 1784.00 = N178400 1.2 8 labourers @ N1440 = N230400 |
|  |  |  |  |  |  |  | N408800 |
| 1 2 | Reinforcement Bars Miscellaneous Transport Handling Charges | High Yield Binding Wire Bars Bars | 9.45 16 9.45 9.45 | Tons Bundles Tons Tons |  |  | 20 gang days 1.1 4Nr fitters @ N 1784 = N142720 1.2 5Nr labourers @ N1440 = N144000 |
|  |  |  |  |  |  |  | N552800 |
|  | Page Total | Wood Nails Bars Binding wire Transport Formwork Reinforcement Nails Handling Charge Formwork Bindingwire Bars nails | 370 20 9.45 15 - - - | lengths bags Tons bundles - - | - - |  |  |
| Formwork and Reinforcement Carried To Summary |  |  |  |  |  |  | N961.600 |

CONSTRUCTION RESOURCE AND ECONOMY SCHEDULE  (CORES)CONTD.

| ITEM REF: NO | WORK SECTION/ ELEMENT DESCRIPTION | EMPLOYER’S RESPONSIBILITY |  |  |  |  | CONTRACTOR’S RESPONSIBILITY |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Materials | Qty | Unit | Price | Amount N K |  |
| 1 | Masonry Block walling | Blocks | 23625 | Nr |  |  | 15 gang days 1.1 11 Masons @ N 1784 = N294360 1.2 17 labourers @ N1440 = N367,200 |
|  |  |  |  |  |  |  | N661,560 |
| 2 2.1 1 2 | Miscellaneous Mortar Finishes Walls Floors | Cement Sand Cement Sand | 299 12 311 12 | bags Trips bags Trips |  |  | 3 days 1.1 1Nr mixer @ N 7000.00 = N21,000.00 |
|  |  |  |  |  |  |  | 20 gang days 1.1 8 Masons @ N 1784 = N285,440 1.2 12 labourers @ N1440 = N345,000 2.1 8Nr mixers @ N7000 = N1,120,000.00 |
|  |  |  |  |  |  |  | N1,750,440.00 |
|  | Transport Handling Charges Page Total | Cement Cement Block walling Mortar Finishes Transport Handling Charge | 610 610 | bags bags |  |  |  |
| Masonry Carried To Summary |  |  |  |  |  |  | N2,380,880 |

SUMMARY OF SOME ELEMENTS

| Page Nr. | Work Description | Employer’s Responsibility | Contractor’s Responsibility |
| --- | --- | --- | --- |
|  | Preliminaries and General Items | - | N157,760.00 |
|  | Site Preparation/Earthworks | - | N 360,000.00 |
|  | Concrete |  | N1,181,752.00 |
|  | Formwork and Reinforcement |  | N961,600.00 |
|  | Masonry |  | N2,380,880.00 |

- Title of the project

- Preliminaries and General items

- Basically in a tabular, divided principally into 3 columns

Column 1 is for Work descriptions accommodating two columns, showing features, nature and other descriptions of the project.

Column 2, often subdivided into Five each showcasing material, quantity, unit, price and amount all designed as Employer’s Responsibilities.

Column 3, is designed as Contractor’s Responsibilities and to capture the skilled and unskilled labour contents including their cost implications (method related statement and charge).

- Cost of labour for each element is either taken to  collection page and/or transferred  to a Summary page culminating to Grand Summary Tender.

Importance Of Resource Scheduling For Construction Industry Development

The construction process is a cobweb of sequentially guided assemblance of numerous separate specialized components/elements underpinned with great diversity of materials input, craft and equipment.

The process is said to be formal when operated under approved policies and regulations and these generate very high but significant multipliers and accelerators whose efficacy impact positively on a nation’s economy.

However, the total cost associated with the formal project procurement processes appears to be exorbitant especially for some private and corporate clients. Incomplete adherence to rules though informal, affords these clients the opportunity of relatively effecting “savings” from most of the costs considered “avoidable”.

These actions, most often attract unpleasant consequences.  Materials, plant and labour which consume about 80% of the Construction Cost by the invocation of intuition get delivered to site prematurely or even in excess thereby resulting to unnecessary storage costs, deterioration (cement may harden), et cetera.

In addition, as certain documents including the Bills of Quantities (specifications and quality source) may not be in reference, poor quality materials and technology often associated with Building and Structural failures find its prevalence in the informal sector. Thus, effecting distortions and/or leakages on the contributions of the construction industry to the Gross Domestic Product.

Arising from above, it becomes imperative to plug these leakages by the introduction of acceptable and affordable tools for the informal sector project procurement processes towards addressing the restraining forces of the formal sector project procurement processes on the nation’s economy.

The “CORES” therefore, serves as antidote, and is soaked with dynamism and several driving forces capable of accommodating the project environment situations in the informal sector procurement processes so as to ensure macro efficiency in the construction industry with its attendant Economic Development.

I am done

Thanks for listening.

Prof. S.I.J Onwusonye FNIQS, CCArb.

March 29, 2021.