## Slide 1: OVERVIEW OF STANDARD METHOD OF RESCOURCE SCHEDULLING HUSSAINI A. DIKKO; FNIQS, PPNIQS RESENTATION TO THE NIGERIA INSTITUTE OF QUANTITY SURVEYORS ON TRAIN THE TRAINERS WORKSHOP

## Slide 2: Resource Schedule documents (RSD) is prepared using Standard Method of Resource Scheduling 1 (SMRS 1) for effective allocation, planning and management of resources
The RSD consist of the followings sections
  Reference/Number
  Description
  Employer’s/ Contractors Responsibility Materials issue
  Contractors Responsibility Method Statement and Charges
 |  | Employer's/Contractors responsibility |  |  |  | Contractors responsibility | 
 |  | Material issue |  |  |  | Method statement and charge | 
Ref/No | DESCRIPTION | Qty | Unit | Rate | Amount | Work Gangs(s) | Plant/Tools Items

## Slide 3: REFERENCE/NUMBER The SMRS document provided reference code for items of works which can be refer for better standardization of the measurement units. DESCRIPTION The document required that a detail description of the work items must be provided which must include the measured quantity of the work item. EMPLOYER’S/ CONTRACTORS RESPONSIBILITY MATERIALS ISSUE This section is the materials analysis where the measured quantity is broken down into various material components with their prices required for the work item. We have the unit, quantities and market prices under this section. The procurement of these materials can either hand by the Employer or the contractor as the case maybe. CONTRACTORS RESPONSIBILITY METHOD STATEMENT AND CHARGES This section is the installation cost of the item of work and charges for tools used for the installation. The Contractor is responsible for the execution and installation of the work items.
STEPS REQUIRED TO PREPARE RESOURCE SCHEDULE ARE :
Designs or Bills of Quantities
Breakdown analysis of the measured quantities into various materials components required
Prevailing Market prices of the various materials
Cost of installation and rent/hire charges for equipment/tools required for the installation

## Slide 4: An example of the Bill of Quantities page

## Slide 5: An example of the breakdown analysis worksheet
The materials components of the various items of work are determine using the standard conversion factor
Example of this factors are:
1m3 of Concrete Grade 15 has 3.5 bags of cement (50kg).
1m3 of concrete grade 20 has 4.3 bag of cement (50kg).

## Slide 6: An example of resource schedule page
Under the Employer’s/contractor responsibility (materials issue) can be procure by either the Employer or the contractor their implications are as follows:

## Slide 7: For the Employer to procure materials for construction means:
The contractor is not responsible for quality of the materials.
the optimization of materials wastage will not be practicable as the contractor is not responsible for material procurement.
The employer must engage a specialist who must advice him on material procurement to ensure that quality is attain and also they have to be additional supervision on the contractor installation to avoid wastages of materials.
For the Contractor to procure materials for construction means:
The contractor is responsible for the quality of the materials.
the contractor can compromise on the quality of the materials in order to maximize his profit.
The Employer must put a frame work of supervision to ensure that proper advice on quality of materials is not compromise in during procurement.

## Slide 8: Contractors responsibility method statement and charges
We assess the contractor method statement and charges with regards to the various installation techniques used in the construction industry.
We then assumed the midway between the mechanize and direct labour cost of installation.
Based on our findings we used the following assumption.
1. installation of reinforcement is N40/kg
2. installation concrete is N3500/m3
3. laying of block wall is N35/block etc
Contractor and artisan normally resist use of the resource schedule document to administer project because it discloses the profit margin the contractor may likely get at the end of the project. In most cases the industry tend to deal with this on the basis of lump sums and lump sums are not useful because they are arbitrary and not realistic. In the event that lump sum is agreed with contractor, the importance of the resource schedule document will serve as a guide to ensure that the lumpsum agreed was based on an informed decision.

## Slide 9: On our estimations for labour cost of installation constants and materials usage, must have to be put to test over time and be refine to be updated so that it can be practical .
The End